## Hoja1
Requirement ID | Requirement Description | Priority | Assigned to | Coverage | Test Case IDs | Level | Execution Status | Defect IDs
REQ-01 | User registration | Must | Jona | Covered | TC-AuthN-01 | Unit (Front) | Passed
[5 empty] | TC-AuthN-02 | Unit (Back) | Passed
[5 empty] | TC-AuthN-03 | Integration | Not run
[5 empty] | TC-AuthN-04 | Integration | Not run
[5 empty] | TC-AuthN-05 | E2E | Not run
[5 empty] | TC-AuthN-06 | E2E | Not run
REQ-02 | User authentication | Must | Jona | Covered | TC-AuthN-07 | Unit (Front) | Passed
[5 empty] | TC-AuthN-08 | Unit (Back) | Passed
[5 empty] | TC-AuthN-09 | Integration | Not run
[5 empty] | TC-AuthN-10 | Integration | Not run
[5 empty] | TC-AuthN-11 | E2E | Not run
[5 empty] | TC-AuthN-12 | E2E | Not run
REQ-03 | API authorization | Must | Jona | Covered | TC-AuthZ-01 | Unit (Back) | Not run
[5 empty] | TC-AuthZ-02 | Integration | Not run
[5 empty] | TC-AuthZ-03 | Integration | Not run
[5 empty] | TC-AuthZ-04 | Integration | Not run
[5 empty] | TC-AuthZ-05 | Integration | Not run
[5 empty] | TC-AuthZ-06 | Integration | Not run
REQ-04 | UI authorization | Must | Jona | Covered | TC-AuthZ-07 | Unit (Front) | Passed
[5 empty] | TC-AuthZ-08 | Integration | Not run
[5 empty] | TC-AuthZ-09 | Integration | Not run
[5 empty] | TC-AuthZ-10 | E2E | Not run
[5 empty] | TC-AuthZ-11 | E2E | Not run
REQ-05 | Duplicate usernames/emails are rejected | Must | Jona | Covered | TC-AuthN-13 | Unit (Back) | Passed
[5 empty] | TC-AuthN-14 | Integration | Not run
[5 empty] | TC-AuthN-15 | Integration | Not run
[5 empty] | TC-AuthN-16 | E2E | Not run
REQ-06 | Anonymous user browses courses | Must | Jona | Covered | TC-CM-01 | Unit (Front) | Passed
[5 empty] | TC-CM-02 | Integration | Not run
[5 empty] | TC-CM-03 | Integration | Not run
[5 empty] | TC-CM-04 | Integration | Not run
[5 empty] | TC-CM-05 | E2E | Not run
[5 empty] | TC-CM-06 | E2E | Not run
REQ-07 | Pagination works correctly | Must | Jona | Covered | TC-CM-07 | Unit (Back) | Not run
[5 empty] | TC-CM-08 | Unit (Front) | Passed
[5 empty] | TC-CM-09 | Integration | Not run
[5 empty] | TC-CM-10 | Integration | Not run
[5 empty] | TC-CM-11 | E2E | Not run
REQ-08 | Admin manages users | Must | Takis | Covered | TC-UserMgmt-01 | Integration | Not run
[5 empty] | TC-UserMgmt-02 | Integration | Not run
[5 empty] | TC-UserMgmt-03 | Integration | Not run
[5 empty] | TC-UserMgmt-04 | Integration | Not run
[5 empty] | TC-UserMgmt-05 | Integration | Not run
REQ-09 | Admin promotes students | Must | Takis | Covered | TC-UserMgmt-06 | Integration | Not run
[5 empty] | TC-UserMgmt-07 | Unit (Back) | Not run
[5 empty] | TC-UserMgmt-08 | E2E | Not run
REQ-10 | Admin manages courses | Must | Takis | Covered | TC-CM-12 | Integration | Not run
[5 empty] | TC-CM-13 | Integration | Not run
[5 empty] | TC-CM-14 | Integration | Not run
[5 empty] | TC-CM-15 | Unit (Back) | Not run
[5 empty] | TC-CM-16 | E2E | Not run
REQ-11 | Admin manages shifts | Must | Takis | Covered | TC-Scheduling-01 | Integration | Not run
[5 empty] | TC-Scheduling-02 | Integration | Not run
[5 empty] | TC-Scheduling-03 | Unit (Back) | Not run
REQ-12 | Admin views reports | Must | Takis | Covered | TC-Reporting-01 | Integration | Not run
[5 empty] | TC-Reporting-02 | Integration | Not run
REQ-13 | Student enrolls in courses | Must | Axel | Not covered |  |  | Not run
REQ-14 | Student unenrolls from courses | Must | Axel | Not covered |  |  | Not run
REQ-15 | Student submits activities | Must | Axel | Not covered |  |  | Not run
REQ-16 | Student views activities and grades | Must | Axel | Not covered |  |  | Not run
REQ-17 | Student completes a course | Must | Axel | Not covered |  |  | Not run
REQ-18 | Professor manages activities | Must | Santino | Not covered |  |  | Not run
REQ-19 | Professor grades submissions | Must | Santino | Not covered |  |  | Not run
REQ-20 | Professor only manages assigned courses | Must | Santino | Not covered |  |  | Not run
REQ-21 | Student schedule conflicts are validated | Must | Santino | Not covered |  |  | Not run
REQ-22 | Professor shift constraints are validated | Must | Santino | Not covered |  |  | Not run